## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [7 empty] | Andrew Bellas | Jonathan Dang | Michael Do | Mohsin Shaik | Total
|  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
| Information Gathering: |  |  |  | 2 |  | 4
Preliminary & Parallel Tasks | Creating preliminary questions to ask Slap Shot Decal | Project Team | Team | 1 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
| Gather Information for Slap Shot Decal | Project Team | (Andrew, Mo) | 1 |  | 2 |  | 1 |  |  | 1 | 2
| Readying Website Builder: |  |  |  | 2 |  | 6
| Installing wordpress and configure to sync data to GitHub | Developer | (Jon,Andrew) | 2 |  | 6 |  | 1 | 5 |  |  | 6
Design & Build | Slap Shot Decal Webpage Layout |  |  |  | 43 |  | 13
Iteration 1: | Order Page | Developer | Mo | 9 |  | 0 | [5 empty] | 0
| Contact Us Page | Developer | Jon | 6 |  | 2 |  |  | 2 |  |  | 2
| About Us Page | Developer | Jon | 6 |  | 3.5 |  |  | 3.5 |  |  | 3.5
| Product Gallery Page | Developer | Michael | 6 |  | 5 |  |  |  | 5 |  | 5
| Home Page | Developer | Andrew | 8 |  | 2 |  | 2 |  |  |  | 2
| Website Header | Developer | Andrew | 8 |  | 0.5 |  | 0.5 |  |  |  | 0.5
Design, Content Implementation & Communication Iteration 2: | Slap Shot Webpage Content & Design |  |  |  | 28 |  | 0
| Order Page | Developer | Mo | 9
| Contact Us Page | Developer | Jon | 7
| About Us Page | Developer | Jon | 7
| Product gallery Page | Developer | Michael | 3
| Home Page | Developer | Andrew | 2
Total |  |  |  | 75 | 75 | 23 | 23 | 5 | 11 | 5.5 | 1.5 | 23